## Sheet1
# | User Stories | Sprints | sprints/hours | Assignation | Actual hours that takes to finish the task
1 | As a first time of user, I want to sign up using an strong password so that no one can hack my account | 1 | 15 Hr | Ahmed | 20 Hr
2 | As a first time of user, I want to View and search for any restaurants without signing in just know the restaurants and if any of them attracted me I'll sign in | 1 | 20 Hr | Mona | 20 Hr
3 | As a signed in user, I want to View the menu and add to the cart what I need and see if there are available in the places in which I ordered from or not | 2 | 15 Hr | Zeinab | 15 Hr
4 | As a signed in user, I want to make an purchase of what I added to cart "cash on delivery" | 3 | 25 Hr | Mohamed | 30 Hr
| As a signed in user, I want to make an purchase of what I added to cart "credit card" | 3 | 25 Hr | Ziad | 25 Hr
5 | As a subscriber resturant, I want to view orders of the clients to start preparing the order and know the way client choose to purchase "Cash on delivery" | 3 | not planned yet | Abdullah
| As a subscriber resturant, I want to view orders of the clients to start preparing the order and know the way client choose to purchase "Credit card" | 3 | not planned yet | Ayman
6 | As a subscriber resturant, I want to let the user know that his/her order is changed to delivered | 3 | not planned yet | Adam